## Sheet1
| Term 4 |  |  |  | Holidays | [5 empty] | Term 1 | [9 empty] | Holidays |  | Term 2
Week | 2017-11-25 | 2017-12-02 | 2017-12-09 | 2017-12-16 | 2017-12-23 | 2017-12-30 | 2018-01-06 | 2018-01-13 | 2018-01-20 | 2018-01-27 | 2018-02-03 | 2018-02-10 | 2018-02-17 | 2018-02-24 | 2018-03-03 | 2018-03-10 | 2018-03-17 | 2018-03-24 | 2018-03-31 | 2018-04-07 | 2018-04-14 | 2018-04-21 | 2018-04-28 | 2018-05-05 | 2018-05-12 | 2018-05-19 | 2018-05-26 | 2018-06-02 | 2018-06-09 | 2018-06-16 | 2018-06-23 | Total: 31 Wks
Game Framework
Research & test existing libraries | bar: 2017-12-09 to 2017-12-23
Library helpers | bar: 2017-12-30 to 2018-01-06
Base runtime (game loop) | bar: 2018-01-06 to 2018-01-13
User input | bar: 2018-01-13
Game Design
Exising game research | bar: 2017-12-02 to 2017-12-16
General style/genre/type | bar: 2017-12-09
Mechanics | bar: 2017-12-23 to 2018-01-06
Levels
Tutorial
Multimedia
Background Music
Sound Effects
Character Design
World Design
User Interface
Documentation
Project description | bar: 2018-01-13
Log | l | i | t | e | r | a | l | l | y | n | o | o | n | e | w | i | l | l | f | i | n | d | t | h | i | s | e | v | e | r | !
Pseudocode
Initial Gantt chart
Final Gantt chart
User manual
Topic permission | [10 empty] | x